## BoardProjeto
AUTISM DATA
Grupo 9 |  | Inicio do projeto: | 2022-09-27
Bruna, Fernando, Jennifer, Luan, Luiza e Rodrigo |  | Hoje: | 2022-09-27
|  | Ajuste semanal: | 1 |  |  | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17 | [6 empty] | 2022-10-24 | [6 empty] | 2022-10-31 | [6 empty] | 2022-11-07 | [6 empty] | 2022-11-14 | [6 empty] | 2022-11-21 | [6 empty] | 2022-11-28 | [6 empty] | 2022-12-05 | [6 empty] | 2022-12-12
 | time axis 2022-09-26 to 2022-12-18
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-09-26 to 2022-12-18
Sprint 2 | bar: 2022-10-25
Controle Gantt | Fernando | 100% | 2022-09-27 | 2022-09-30 | 4 | bar: 2022-10-25
Dicionario de dados | Bruna e Luiza | 100% | 2022-09-27 | 2022-09-30 | 4 | bar: 2022-10-25
OKR - Grupo | Jennifer | 100% | 2022-09-27 | 2022-10-02 | 6 | bar: 2022-10-25
Implementação LGPD - parte 1 | Rodrigo | 100% | 2022-09-29 | 2022-10-14 | 16 | bar: 2022-10-09; 2022-10-25
IOT – Refatorar código de geração (mensagens de erro/alerta, etc..) | Bruna | 100% | 2022-09-30 | 2022-10-20 | 21 | bar: 2022-10-09; 2022-10-25
Gerar dados para incrementar bases escolhidas - Python(Pandemia e Alimentar) | Luan | 100% | 2022-09-30 | 2022-10-24 | 25 | bar: 2022-10-09; 2022-10-25
Cleaning da tabela Alimentar pyspark | Jennifer e Fernando | 100% | 2022-09-30 | 2022-10-24 | bar: 2022-10-09; 2022-10-25
Cleaning da tabela Pandemia pyspark | Jennifer e Fernando | 100% | 2022-09-30 | 2022-10-10 | 11 | bar: 2022-10-09; 2022-10-25
Documentação de definição de redes IOT | Grupo | 100% | 2022-09-30 | 2022-10-10 | bar: 2022-10-09; 2022-10-25
Conectar IOT ao AZURE | Grupo | 100% | 2022-09-30 | 2022-10-10 | bar: 2022-10-09; 2022-10-25
Gestão e controle de entregaveis | Luiza | 100% | 2022-09-30 | 2022-10-24 | 25 | bar: 2022-10-09; 2022-10-25
Phase 2 Title
Integração Azure AWS |  | 100% | 17/11/2022 | 25/11/2022 | #VALUE! | bar: 2022-11-17 to 2022-11-24; 2022-12-06
Revisar/Terminar Cleaning |  | 100% | 17/11/2022 | 25/11/2022 | #VALUE! | bar: 2022-11-17 to 2022-11-24; 2022-12-06
Revisar LGPD |  | 100% | 17/11/2022 | 25/11/2022 | #VALUE! | bar: 2022-11-17 to 2022-11-24; 2022-12-06
Criar tabelas fato-dimensão |  | 100% | 17/11/2022 | 25/11/2022 | #VALUE! | bar: 2022-11-17 to 2022-11-24; 2022-12-06
Azure Stream Analytics |  | 100% | 25/11/2022 | 2022-06-12 | bar: 2022-11-25 to 2022-12-06
Criar Big Numbers |  | 100% | 25/11/2022 | 2022-06-12 | bar: 2022-11-25 to 2022-12-06
Criação da arquitetura final |  | 100% | 25/11/2022 | 2022-06-12 | bar: 2022-11-25 to 2022-12-06
Complementar apresentação |  | 100% | 2022-02-12 | 2022-06-12 | 121 | bar: 2022-12-02 to 2022-12-06
Phase 3 Title
Task 1 |  |  | 2019-01-16 | 2019-01-21 | 6
Task 2 |  |  | 2019-01-22 | 2019-01-26 | 5
Task 3 |  |  | 2019-01-27 | 2019-02-01 | 6
Task 4 |  |  | 2019-02-02 | 2019-02-06 | 5
Task 5 |  |  | 2019-01-27 | 2019-01-31 | 5
Phase 4 Title
Task 1 |  |  | 2019-01-29 | 2019-02-03 | 6
Task 2 |  |  | 2019-01-29 | 2019-02-02 | 5
Task 3 |  |  | 2019-02-03 | 2019-02-06 | 4
Task 4 |  |  | 2019-02-03 | 2019-02-06 | 4
Task 5 |  |  | 2019-02-07 | 2019-02-11 | 5
Phase 5 Title
Task 1 |  |  | 2019-02-05 | 2019-02-10 | 6
Task 2 |  |  | 2019-02-05 | 2019-02-07 | 3
Task 3 |  |  | 2019-02-08 | 2019-02-13 | 6
Task 4 |  |  | 2019-02-08 | 2019-02-13 | 6
Task 5 |  |  | 2019-02-08 | 2019-02-12 | 5
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.